## FMEA
Potential Failure Mode & Effects Analysis
Process/Product: |  |  | Learning Management Platform (LMS) Migration |  |  |  |  | FMEA Date: (original) |  |  |  |  | 2024-11-23
FMEA Team: |  |  | Ukunoritsemofe Edema , IT Team and Key Stakeholders |  |  |  |  | (Revised) |  |  |  |  | 2024-11-24
Responsibility: |  |  | Ukunoritsemofe Edema, IT Team and Stakeholders |  |  |  |  | Page: |  |  |  |  | 1 |  | of |  |  | 1
Prepared By: |  |  | Ukunoritsemofe Edema
Process | [10 empty] | Actions |  |  |  |  | Results
Process Steps or Product Functions | Potential Failure Mode | Potential Effects of Failure |  | Severity (1-10) | Potential Cause(s) of Failure | Occurrence (1-10) | Current Controls |  | Detection (1-10) | Risk Priority Number (RPN) | Recommended Action | Responsibility and Target Completion Date |  | Action Taken |  | Revised Severity (1-10) | Revised Occurrence (1-10) | Revised Detection (1-10) | Revised Risk Priority Number
Course Content: Loss of Formating or Multimedia Elements | Improper rendering of fonts, layouts, or multimedia files. i.e. videos and images. | course materials may be less engaging without proper formatting, images, or videos. |  | 5 | Incompatibility between LMS platforms or file formats. | 5 | Pre-migration format compatibility checks. |  | 6 | 150 | Use migration tools that preserve formatting or reformat content post-migration | IT Team & Instructors, 2 weeks before migration |  | Conducted a pilot test with a sample course to identify and address formatting issues |  | 4 | 4 | 4 | 64
Course Content: Broken Links | Hyperlinks to external resources or internal course materials become invalid post-migration. | Students cannot access essential readings or resources, hindering their learning experience. |  | 5 | Changes in URL structure during migration | 6 | Automated link validation tools. |  | 4 | 120 | Perform a complete link audit and fix broken links before LMS launch. | IT Team, 1 month before launch |  | Implemented a script to identify broken links and updated them |  | 3 | 3 | 3 | 27
Course Content:Incomplete Content Migration | Some course modules or documents fail to transfer due to size or compatibility issues. | Missing modules or materials disrupt the course flow and learning outcomes. |  | 7 | Large file sizes or unsupported content types | 4 | Regular backups of course materials |  | 5 | 140 | Break large files into smaller segments and ensure all content types are supported in the new LMS | IT Team, 3 weeks before migration |  | Uploaded oversized files to cloud storage and linked them to LMS modules. |  | 5 | 3 | 4 | 60
Course Content:SCORM File Corruption | SCORM-compliant content may not be fully functional in the new system. | Inability to record completion of SCORM activities can impact grades and feedback. |  | 7 | File compatibility issues or improper upload processes. | 4 | SCORM validation tools and pre-migration testing |  | 4 | 112 | Test all SCORM content in a sandbox environment and convert files to compatible formats if necessary. | IT Team, 2 weeks before migration |  | Validated SCORM content for functionality in the new LMS and fixed errors. |  | 6 | 3 | 4 | 72
Student Data Privacy | Personal data exposed during the migration process due to inadequate encryption. | Breach of laws like GDPR or FERPA, leading to fines and sanctions |  | 10 | Insufficient encryption or access control during migration. | 3 | Secure data transfer protocols and encryption. |  | 7 | 210 | Implement multi-factor authentication (MFA) and perform penetration testing to identify vulnerabilities | IT Team & Security Team, 2 months before migration |  | Configured MFA for all accounts and conducted a penetration test. |  | 9 | 2 | 3 | 54
Student Data Loss | Partial or total loss of student grades, progress, or submissions. | Loss of grades, feedback, or submissions can impact student evaluations. |  | 9 | Incorrect backup procedures or system failures during migration | 3 | Regular backups and redundancy in storage systems. |  | 5 | 135 | Use a robust data migration tool with error logging and conduct pre- and post-migration audits. | IT Team, 1 week before migration |  | Verified all backups and conducted a post-migration data validation audit. |  | 8 | 2 | 3 | 48
Student Data: Progress Tracking | Mismatches in student profiles, such as associating grades with the wrong students. | Students may receive incorrect grades, leading to disputes. Or Time-consuming efforts required to audit and correct data errors. |  | 8 | Improper field matching or configuration errors. | 4 | Data mapping templates and field validation. |  | 4 | 128 | Conduct a data mapping workshop with stakeholders and perform mock migrations to validate data integrity. | IT Team & Stakeholders, 1 month before migration |  | Held workshops to align field mappings and conducted a test migration. |  | 6 | 3 | 4 | 72
User Accounts: Login Credentials | Users unable to log in due to password mismatches or corrupted credentials. | Users unable to log in, missing classes or deadlines. |  | 6 | Password mismatches or incomplete credential migration | 6 | Authentication testing pre-migration. |  | 6 | 216 | Implement a password reset process and communicate with users in advance about potential issues. | IT Team & Admin Team, 2 weeks before migration |  | Provided users with instructions for resetting passwords. |  | 4 | 3 | 3 | 36
User Accounts | Permissions or roles (e.g., student, instructor, admin) are incorrectly assigned after migration. | IT services may be overwhelmed with password reset requests. |  | 8 | Misconfigured user roles or insufficient testing of role assignments. | 5 | Manual role validation post-migration. |  | 5 | 200 | Automate role mapping and test different user scenarios to ensure accurate role assignment. | IT Team, 1 month before migration |  | Automated role assignment scripts were tested and validated. |  | 5 | 3 | 4 | 60
System Settings: Access Controls | Default permissions or access levels are altered, causing unauthorized access or restricted access to key features. | Sensitive data may be accessible to all users, increasing risk of misuse. |  | 9 | Improper role permissions or incomplete policy transfer. | 4 | Role-based access control policies in place. |  | 6 | 216 | Test role permissions in a staging environment and audit access logs post-migration. | IT Team & Security Team, 1 week before launch |  | Staging environment role tests completed and access logs reviewed |  | 7 | 3 | 4 | 84
Sstem Settings: Integrations | Third-party tools like Turnitin, Zoom, or Microsoft Teams fail to integrate with the new platform. | Tools like Turnitin or Zoom may not function, affecting assignments and virtual classes. |  | 7 | API incompatibility or changes in tool configurations. | 6 | API testing and validation tools. |  | 5 | 210 | Update APIs and configurations to ensure compatibility with the new LMS. | IT Team, 3 weeks before migration |  | API configurations were updated and tested for all third-party tools |  | 5 | 4 | 4 | 80
Analytics & Reports: Usage Statistics | Analytics dashboards fail to display accurate information due to discrepancies in migrated data. | Misallocation of Resources based on faulty data, leading to inefficiencies. |  | 6 | Mismatched fields or reporting tool incompatibility. | 4 | Mock reporting and validation of migrated data. |  | 5 | 120 | Cross-check reports against original data and adjust reporting tools as necessary. | IT Team, 2 weeks after launch |  | Adjusted reporting configurations to match original data fields. |  | 4 | 3 | 3 | 36
Analytics & Reports: Course Insights | Engagement or progress tracking data becomes unreadable or incomplete. | Inability to analyze trends in student performance over time. |  | 8 | Errors during data transfer or incorrect data formats. | 3 | Data backups and checksum validation. |  | 6 | 144 | Perform data integrity checks using checksum tools and conduct multiple validation rounds. | IT Team, 1 week before launch |  | Data integrity checks completed, and discrepancies resolved |  | 6 | 2 | 3 | 36
Communication Tools: Email/Message Logs | Communication records between instructors and students are missing or incomplete. | Important information, feedback, or instructions may be lost which may lead to difficulty in resolving misunderstandings without records. |  | 6 | Incomplete log exports or unsupported formats. | 3 | Backups of communication logs. |  | 4 | 72 | Export all logs in a universally compatible format and verify import success in the new system | IT Team, 2 weeks before migration |  | Exported logs in compatible formats and tested imports in sandbox environments. |  | 5 | 2 | 3 | 30
Communication Tools: Annoucements | Announcements become outdated, inaccessible, or lose their intended audience tags. | Students may miss critical updates about assignments or schedule changes leading to disconnection from the course. |  | 4 | Incorrect tagging of announcements or migration scripts failing to include them. | 5 | Pre-migration announcement review. |  | 4 | 80 | Validate announcements with tags in a test environment and update configurations if needed. | IT Team & Instructors, 2 weeks before migration |  | Manually reviewed and corrected announcement tagging in the migrated LMS |  | 3 | 3 | 4 | 36
Score | Severity Guidelines
| AIAG |  | Six Sigma
10 | Hazardous without warning |  | Injure a customer or employee | [5 empty] | Bad
9 | Hazardous with warning |  | Be illegal
8 | Very High |  | Render product or service unfit for use
7 | High |  | Cause extreme customer dissatisfaction
6 | Moderate |  | Result in partial malfunction
5 | Low |  | Cause a loss of performance which is likely to result in a complaint
4 | Very Low |  | Cause minor performance loss
3 | Minor |  | Cause a minor nuisance but can be overcome with no performance loss
2 | Very Minor |  | Be unnoticed and have only minor effect on performance
1 | None |  | Be unnoticed and not affect the performance | [5 empty] | Good
Score | Occurrence Guidelines
| AIAG |  |  | Six Sigma
10 | Very High: Persistent Failures, Ppk < 0.55 |  |  | More than once per day |  | > 30% |  |  | Bad
9 | Very High: Persistent Failures, Ppk >= 0.55 |  |  | Once every 3-4 days |  | < 30%
8 | High: Frequent Failures, Ppk >= 0.78 |  |  | Once every week |  | < 5%
7 | High: Frequent Failures, Ppk >= 0.86 |  |  | Once per month |  | < 1%
6 | Moderate: Occasional Failures, Ppk >= 0.94 |  |  | Once every 3 months |  | < 0.03%
5 | Moderate: Occasional Failures, Ppk >= 1.00 |  |  | Once every 6 months |  | < 1 per 10,000
4 | Moderate: Occasional Failures, Ppk >= 1.10 |  |  | Once per year |  | < 6 per 100,000
3 | Low: Relatively Few Failures, Ppk >=1.20 |  |  | Once every 1-3 years |  | < 6 per million
2 | Low: Relatively Few Failures, Ppk >=1.30 |  |  | Once every 3-6 years |  | < 3 per 10 million
1 | Remote: Failure is Unlikely, Ppk >=1.67 |  |  | Once every 6-9 years |  | < 2 per billion |  |  | Good
Score | Detection Guidelines
| AIAG |  |  |  | Six Sigma
10 | Almost Impossible: Absolute certainty of non-detection |  |  |  | Defect caused by failure is not detectable |  |  |  | Bad
9 | Very Remote: Controls will probably not detect |  |  |  | Occasional units are checked for defects
8 | Remote: Controls have poor chance of detection |  |  |  | Units are systematically sampled and inspected
7 | Very Low: Controls have poor chance of detection |  |  |  | All units are manually inspected
6 | Low: Controls may detect |  |  |  | Manual inspection with mistake-proofing modifications
5 | Moderate: Controls may detect |  |  |  | Process is monitored (SPC) and manually inspected
4 | Moderately High: Controls have a good chance to detect |  |  |  | SPC is used with an immediate reaction to out of control conditions
3 | High: Controls have a good chance to detect |  |  |  | SPC as above, 100% inspection surrounding out of control conditions
2 | Very High: Controls almost certain to detect |  |  |  | All units are automatically inspected
1 | Very High: Controls certain to detect |  |  |  | Defect is obvious and can be kept from affecting the customer |  |  |  | Good